## Sheet1
Sno | Task Name | Page | Assigned To | Satus | Comments
1 | Server configuration | Application |  | Completed
2 | DB configuration |  |  | In Progress
3 | Login UI | Login page | Imran | Completed
4 | Login data validation |  | Deepak
5 | Seat layout - HTML | Seat Selection Page | Reddy | Completed
6 | Seat layout - JSP |  | Imran
7 | Seat selction insertion to table |  | Deepak
8 | Seat Check out |  | Imran
9 | Front End alignments | Application | Eswar